## Tasks
Task | Category | Date | Category prio | WIP | Done | Notes
Framework for GUI (sidebar, buttons, plots, time slider) | GUI | 2022-08-18 | 0
Restructure pyshape packege: see pyshape tab | Geometry | 2022-08-19 | 0
Abstract functions in pyshape | Geometry | 2022-08-19 | 0
Cleanup __init__ files and references | Structure | 2022-08-22 | 0
Restructure analysis class | Analysis | 2022-08-23 | 0 |  |  | base class with two implementations, one for pygame plots and one for matplotlib plots. Analysis class should handle plotting, and specific plots can be added with an add_plot method. Define inputs and outputs of analysis!
Move application / ticker to GUI package and inhertit in project. | GUI | 2022-08-18 | 1 |  | x
Support for more complex genomes | Bots | 2022-08-24 | 0 |  |  | Not only NN parameters, but also bot attributes such as size or speed.
Restructure simulation class, more logical placement of next_batch/evolve | Simulation | 2022-08-18 | 0
Sidebar to GUI | GUI | 2022-08-18 | 1 |  |  | "container" element. Replaces sidebar. Can extend and retract. Holds other GUI elements and can hold user-defined other stuff such as plots. Al GUI must be placed in container?
Docstrings in all modules | Structure | 2022-08-18 | 1
Split application package into different use cases: normal application and SimApp | GUI | 2022-08-22 | 1
Circle and wedge classes | Geometry |  | 1 |  |  | Based on polygon, at first the only differences is their method for instantiating
Restructure visual testing module | Geometry | 2022-08-19 | 1 |  |  | Add support for circles and wedges, simplify repeat code
Analysis class keeps data instead of plots: | Analysis | 2022-08-18 | 2 |  | x | Not a good idea
Debug bot in individual class instead of population | Bots | 2022-08-23 | 1 |  |  | bool is_debug_bot for individual, and property (get) for population class which loops over all bots and returns the bot that has is_debug_bot enabled.
Restructure analysis plot classes | Analysis | 2022-08-24 | 1 |  |  | ABC template and remove duplicate code,
Scope handling in plots, not in analysis class | Analysis | 2022-08-24 | 1 |  |  | Scope class with the different scope constants. Each plot has a scope from this scope class. Plots get updated from analysis with the current scopes for the current tick, and plots determine themselves wether or not they update or reset.
Standalone neural network package | Network | 2022-08-18 | 1
Numba optimization for domain testing functions | Plotting | 2022-08-19 | 1
Abstract classes for plots module | Plotting | 2022-08-19 | 1
Tune parameters for genetic algorithm for herbivore population | Evolution | 2022-08-24 | 1 |  |  | Currently not very succesful evolution (after adding vitality)
Text info on generation and batch in screen. | GUI | 2022-08-18 | 2
Abstract classes for inheritance in all modules | Structure | 2022-08-18 | 2
Line-circle collision | Geometry | 2022-08-19 | 2 |  |  | https://www.baeldung.com/cs/circle-line-segment-collision-detection https://stackoverflow.com/questions/8968591/circle-polygon-intersections
Polygon-circle colision | Geometry | 2022-08-19 | 2
Point-circle contain detection | Geometry | 2022-08-19 | 2
Simpler hitboxes for bots in the pyshape package. Implement for eating and collisions. | Geometry | 2022-08-18 | 2
Nr runs and nr batches set in GUI | GUI | 2022-08-18 | 4 |  | x | Parameters should be set from file or code, not in GUI
Only draw and update plots when sidebar is extended | Analysis | 2022-08-18 | 2
Streamline network drawing function in network class | Network | 2022-08-18 | 2
Bots can spawn in objects | Bug | 2022-08-18 |  |  | x | Not fixed?
Eating animation and/or growing bots if they eat | Populations | 2022-08-18 |  |  | x | Done with coloring for vitality
Starvation with bot coloring based on its level | Populations | 2022-08-18 |  |  | x
Standalone pygame GUI package | Structure | 2022-08-18 |  |  | x
Fitness generation plot start with [0,0] | Bug | 2022-08-18 | 3
More bot / population types | Features | 2022-08-18 |  |  | x | Moved to ideas
Matplotlib plots for standalone simulation all in single figure | Analysis | 2022-08-18 | 3
Split adding data and checking inscope points in plots? | Plotting | 2022-08-19 | 3 |  |  | Check for other solutions.
Debug bot arrow control | Bots | 2022-08-19 | 3 |  |  | Note: only application implementation needed. See "application_old" in archive
New population / environment | Populations | 2022-08-18 |  |  | x | Moved to ideas
Two competing populations in the same environment | Populations | 2022-08-18 |  |  | x | Moved to ideas
More complexity for populations to encourage different strategies (see ideas) | Populations | 2022-08-18 |  |  | x | Moved to ideas
Refined speed control in GUI | GUI | 2022-08-18 | 4
Restructure as package: projects can import ABCs and implement analyses, bots and pops | Structure | 2022-08-18 | 4
Clustering genomes to identify different species | Analysis | 2022-08-18 | 4 |  |  | Can be done either on full genome or on specific characteristics such as size
Standalone sim: Grid search with avg/max plots for each option averaged over multiple runs | Evolution | 2022-08-18 | 4
Circular hitboxes for faster computing | Bots | 2022-08-18 | 4 |  |  | First complete pyshape tasks
Save and load populations with pickle | GUI | 2022-08-18 | 9
Time control | GUI | 2022-08-19 |  |  | x | Duplicate
Dropdowns for analysis plots in GUI | GUI | 2022-08-18 | 9
Change float64 / int64 to 32 | Geometry | 2022-12-26 | 4 |  | x | Breaks stuff
module __init__ docstrings | Geometry | 2022-12-26 | 3
ABC and abstractmethods for geometrybase | Geometry | 2022-12-26 | 2

## Ideas
Ideas for herbivore population
Bots have size. A size makes bots slower but allows them to go longer without food.
Encourages different strategies: slower = more survivability, faster = more food
Gravity simulator with bots preventing crashes
N-body simulation with planets and arrowbots
Fitness based on survival time
Bots can accelerate and turn, not deccalarate
Flock bots
Bots get higher fitness for flocking together and moving in the same direction
Different populations -> negative fitness for flocking with wrong population
Ideas for sizes of population?
Bot collisions kill both parties
Racing sim
Use image as map with marker for start and gates
Borders: Black/white
Start: Blue pixel with red pixel for direction
How to do collisions? Open cv edge detection, convert shapes to polygons
Actual problem
TSP
Vehicle routing
Network design
Physics simulation
Pymunk as engine
Balancing problem

## Pyshape
Shapes |  | Status | Description
| Line | Done
| Polygon | Done
| Circle | WIP | Same as polygon but with more efficient interaction + rotation
| Wedge | TODO | Same as polygon but with more efficient interaction + rotation
Tools |  | Status | Description
| Edgedata | WIP | Double looping? Check in intersection functions. Possibly split in smaller parts
| Domain | Done
Intersection
coordinates
|  | line | polygon | circle
| line | Done | Optimize | Todo | Optimzation: remove get_edgedata function (double looping!)
| polygon |  | Optimize | Todo
| circle |  |  | Todo
boolean_single
|  | line | polygon | circle
| line | Optimize | Optimize | Todo
| polygon |  | Optimize | Todo
| circle |  |  | Todo
contains
|  | polygon | circle | wedge
| point | Done | Todo | Todo | Circle: just d(center, point) < radius
Wedge: circle AND between angles (used for sensors)
wedge:
Defined by a point, radius and two angles